## Sheet1
System Name | CareSynch (Health Care Appointment Management System)
Members:
Abarquez, Mykha T.
Baruc, Leilah
Tumungha, Hara Alexa
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Project Planning | Abarquez, Baruc, Tumungha | August 15, 2024 | September 26,2024 | Done
2. UI/UX Design | Abarquez, Baruc, Tumungha | September 27, 2024 | October 10, 2024 | Done
3. Frontend Development |  | October 10, 2024 |  | In-Progress
3.1 Login and Register | Tumungha | October 10, 2024 |  | In-Progress
3.2 Appointment History | Baruc | October 10, 2024 |  | In-Progress
3.3 Appointment Form | Baruc | October 10, 2024 |  | In-Progress
3.4 Calendar Integration | Abarquez | October 10, 2024 |  | In-Progress
3.5 Choose Doctor | Baruc | October 10, 2024 |  | In-Progress
3.6 Payment | Abarquez | October 10, 2024 |  | In-Progress
3.7 Profile | Tumungha | October 10, 2024 |  | In-Progress
4. Backend Development of Features
4.1 Login and Register | Tumungha | October 10, 2024 |  | In-Progress
4.2 Appointment History | Baruc | October 10, 2024 |  | In-Progress
4.3 Appointment Form | Baruc | October 10, 2024 |  | In-Progress
4.4 Calendar Integration | Abarquez | October 10, 2024 |  | In-Progress
4.5 Choose Doctor | Baruc | October 10, 2024 |  | In-Progress
4.6 Payment | Abarquez | October 10, 2024 |  | In-Progress
4.7 Profile | Tumungha | October 10, 2024 |  | In-Progress